## risk register
Risk Register
A risk register board for tracking, assessing, and managing potential risks related to the Meals with Impact project.
RISK REGISTERS
Name | Subitems | Notes | Item ID (auto generated)
Introduction |  | The Risk Registers below capture MWI's key identified risks across eight categories. Each risk is rated using the Likelihood (L) and Consequence (C) scales defined in the Framework (Section 3), producing an Inherent rating (before controls) and a Residual rating (after controls). | 11730758098
Subitems | Name | Category | Risk Description | Existing Controls | Likelihood | Consequence | Inherent Risk | Status | Treatment/Action | People | Residual Rating | Residual Risk | Status | Item ID (auto generated)
| L = Likelihood | 1 Rare - 5 Almost Certain |  |  |  |  | 0 | [6 empty] | 11730765656
| C = Consequence | 1 Insignificant → 5 Catastrophic |  |  |  |  | 0 | [6 empty] | 11730779648
| Score = L × C | E = Extreme (20–25) H = High (12–19) M = Medium (6–11) L = Low (1–5) |  |  |  |  | 0 | [6 empty] | 11730762121
| Owner | CEO = Chief Executive Officer ¦ BOD = Board of Directors ¦ MGT = Management ¦ FIN = Finance |  |  |  |  | 0 | [6 empty] | 11730786713
| Status | Status: Active = in progress ¦ Planned = scheduled ¦ Ongoing = continuous control ¦ Complete = addressed |  |  |  |  | 0 | [6 empty] | 11730779969
Register 1: Strategic Risks |  |  | 11730799157
Subitems | Name | Category | Risk Description | Existing Controls | Likelihood | Consequence | Inherent Risk | Status | Treatment/Action | People | Residual Rating | Residual Risk | Status | Item ID (auto generated)
| S1 | Strategic | Entity consolidation fails or is delayed — Pty Ltd and Foundation unable to merge within 12 months, leaving hybrid structure that impedes grant applications and investor confidence | Minter Ellison engaged; Pitcher Partners financial support; Board oversight of legal process | 4 | 4 | 16 | HIGH | Establish clear milestone plan with Minter Ellison; Board to receive monthly status update until complete; contingency plan for delayed completion |  | 9 | MEDIUM | ACTIVE | 11730815381
| S2 | Strategic | Major tender loss — MWI fails to secure Lendlease Arden or South Melbourne social housing tender, impacting revenue growth trajectory | Existing Lendlease relationship (SIK/Victoria Harbour); sector experience; track record in catering | 3 | 4 | 12 | HIGH | Develop a compelling tender submission strategy; ensure entity structure clarity before submission; engage Board networks in tender support |  | 6 | MEDIUM | ACTIVE | 11730969324
| S3 | Strategic | National expansion in the ready-made meals market is advancing faster than MWI's current staffing, systems, and financial resources can handle. | CEO Churchill Fellowship to research model | 4 | 4 | 16 | HIGH | Board to approve growth milestones; pilot must prove unit economics before scaling; conduct capacity assessment prior to launching new sites; monthly updates to continue. |  | 6 | MEDIUM | ACTIVE | 11730967425
| S4 | Strategic | Mission drift occurs as commercial pressures lead MWI to prioritize revenue over employment outcomes for CALD women, impacting program focus and effectiveness. | Mission embedded in Board charter and CEO KPIs; Foundation structure provides charitable purpose anchor | 2 | 5 | 10 | MEDIUM | Board will track employment placement KPIs at every meeting and include mission alignment in reviews of new commercial initiatives. |  | 4 | LOW | ACTIVE | 11730978705
| S5 | Strategic | Closing the Docklands café without a confirmed new CV programme location disrupts operations, lowers delivery capacity, and affects revenue. | Lease ends around May 2026; closure depends on site move; GoGet account supports interim logistics. | 4 | 3 | 12 | HIGH | Identify alternate CV site by Feb 2026; negotiate lease novation with Minters for SIK; Board to approve closure timing; provide monthly status updates. |  | 6 | MEDIUM | ACTIVE | 11731026427
Register 2: Financial Risks |  |  | 11730774318
Subitems | Name | Category | Risk Description | Existing Controls | Likelihood | Consequence | Inherent Risk | Status | Treatment/Action | People | Residual Rating | Residual Risk | Status | Item ID (auto generated)
| F1 | Financial | Outstanding ATO liability of $63,155 (down from $93,434) continues to accrue interest and limits access to grants and financing options. | Loan application prepared with a 6.5% rate over 3 years, showing steady repayments since February 2025, outperforming the 13% ATO rate. | 3 | 4 | 12 | HIGH | Finalise and lodge SELF application; obtain Board approval for loan terms; ensure Pty Ltd solvency maintained; monthly financial reporting to CEO |  | 6 | MEDIUM | PLANNED | 11731013180
| F2 | Financial | The foundation faces a financial challenge with expenses of $566K exceeding revenues of $527K, resulting in a deficit of $124,573. Continued losses at this rate may jeopardize its ability to operate sustainably. | Pitcher Partners financial oversight; Pitcher going concern note in accounts; donations and grants diversification underway | 4 | 4 | 16 | HIGH | Achieve budget surplus in FY2026; review all expense lines for reduction; increase CV and SIK revenue; Board to review monthly management accounts |  | 9 | MEDIUM | ON GOING | 11731030313
| F3 | Financial | The company faces risk due to heavy dependence on a single revenue source, the corporate volunteering program, which has grown 150% year-to-date but remains vulnerable to economic fluctuations. | Four revenue streams (CV, catering, café/SIK, grants); CV diversified across multiple corporate clients | 3 | 4 | 12 | HIGH | Develop at least 2 additional major corporate CV clients; expand SIK to additional sites; close café only when CV alternative is operational |  | 6 | MEDIUM | ACTIVE | 11731034696
| F4 | Financial | Grants income falls — grants and donations declined from $402K (Pty Ltd, FY2024) to $14K (FY2025), indicating shift to commercial model but risk of funding gap if revenue targets missed | Entity consolidation will improve grant eligibility; Foundation grants $462K in FY2025; QBE Foundation relationship active | 3 | 4 | 12 | HIGH | Diversify grant applications under consolidated Foundation; develop new funder relationships; Board members to support grant door-opening |  | 6 | MEDIUM | PLANNED | 11731018069
| F5 | Financial | Related party loans — Harris Ryan ($20,805), Nikki Blanch ($18,147), and Rachael Hua ($2,386) have loans to the Foundation; Pty Ltd owes $27,291 to Foundation | Loans documented in financial statements; Pitcher Partners oversight; informal arrangements being formalised | 2 | 4 | 8 | MEDIUM | Formalise all related party loan agreements with proper terms; Board (non-conflicted members) to approve terms; manage conflicts of interest carefully |  | 3 | LOW | ON GOING | 11731041480
| F6 | Financial | Cash flow crisis — both entities have low cash reserves (Foundation $50,790; Pty Ltd $49,867) relative to monthly payroll obligations ($43K+ per month for Foundation) | Monthly payroll managed; superannuation provisions maintained; Pitcher Partners cash flow monitoring | 3 | 4 | 12 | HIGH | Implement 13-week rolling cash flow forecast; CEO to report cash position to Board monthly; maintain minimum $30,000 cash buffer policy |  | 6 | MEDIUM | PLANNED | 11731036268
Register 3: Operational Risks |  |  | 11730790556
Subitems | Name | Category | Risk Description | Existing Controls | Likelihood | Consequence | Inherent Risk | Status | Treatment/Action | People | Residual Rating | Residual Risk | Status | Item ID (auto generated)
| O1 | Operational | Kitchen food safety incident — Prahran kitchen production error causes food contamination, foodborne illness, or recall affecting programme participants, customers, or catering clients | Head Chef (Camille Petit) engaged; kitchen transition completed; food safety systems in place | 2 | 5 | 10 | MEDIUM | Implement HACCP-compliant food safety plan; regular food safety training for all kitchen staff; food safety audit twice annually; incident reporting protocol |  | 4 | LOW | ACTIVE | 11731039517
| O2 | Operational | SIK technology failure — Social Impact Kiosk at Victoria Harbour experiences extended technical failure (Spanish supplier, long resolution times noted in minutes) impacting revenue and client relationship | Supplier relationship maintained; Lendlease engagement strong; exploring alternate machine options | 4 | 3 | 12 | HIGH | Identify backup machine supplier; negotiate service level agreement with Spanish supplier; develop SIK downtime protocol; Harris to research alternatives via Fellowship |  | 6 | MEDIUM | PLANNED | 11731031232
| O3 | Operational | Unreliable courier and delivery services for catering, ready meals, and inter-site food transfers are causing disruptions to commercial operations. | GoGet electric vehicle account set up; internal driver applications underway; funding requests for electric vehicles are active to enhance delivery efficiency. | 4 | 3 | 12 | HIGH | Prioritise procurement of MWI vehicle (electric); maintain at least 2 courier service agreements; develop delivery schedule optimisation |  | 4 | LOW | ON GOING | 11731011143
| O4 | Operational |  |  |  |  | 0 | [6 empty] | 11731042519
| O5 | Operational |  |  |  |  | 0 | [6 empty] | 11731016670
Register 4: People & Culture Risks |  |  | 11730814834
Subitems | Name | Category | Risk Description | Existing Controls | Likelihood | Consequence | Inherent Risk | Status | Treatment/Action | People | Residual Rating | Residual Risk | Status | Item ID (auto generated)
| P1 | People | MD key person risk — Harris Ryan is sole director of Pty Ltd, and primary relationship holder for major funders, partners, and programme. 7-week Churchill Fellowship absence in 2026 creates operational gap. | Rachael Hua, COO oversees operations, marketing and communications. Sofia Neale CFO, manages finances, HR and Programs. | 5 | 5 | 25 | EXTREME | Board to approve CEO succession plan prior to meeting 2 2026; CEO briefing protocol for Board Chair; document key relationships and processes; delegate operational authority during absence; |  | 12 | HIGH | ACTIVE | 11764768554
| P2 | People | Staff retention — loss of Head Chef (Camille Petit) or key programme staff disrupts kitchen quality, production capacity, and employment outcomes for women | Competitive remuneration; positive culture; new kitchen environment a retention factor | 3 | 4 | 12 | HIGH | Develop retention strategy for key roles; document role procedures; cross-train staff where possible; Board to be informed of any senior departure |  | 6 | MEDIUM | PLANNED | 11764770270
| P3 | People | Participant safeguarding — programme participants include women from refugee and CALD backgrounds who may be experiencing trauma, family violence, or exploitation | Trauma-informed programme design; cultural safety embedded in operations; referral pathways to support services | 2 | 5 | 10 | MEDIUM | Implement formal safeguarding policy; train all staff in trauma-informed practice; establish confidential reporting mechanism; review annually |  | 4 | LOW | PLANNED | 11764784264
| P4 | People | Volunteer and contractor management — corporate volunteers (10 per session) and contractors present WHS and safeguarding risks if not appropriately inducted. | CV programme well-established; session structure provides supervision; pricing model covers coordination costs, volunteer insurance active. | 3 | 2 | 6 | LOW | Formalise volunteer induction process; update WHS protocols for CV sessions; ensure adequate staff |  | 3 | LOW | ACTIVE | 11764779950
| P5 | People | Board director duties — new Board of Directors, many in first formal director roles, may not fully understand legal duties, conflict of interest obligations, or ACNC responsibilities | AICD trained Director (Rod Szigeter); QBE skilled volunteer project support; Director Consent Forms signed; Conflict of Interest Register maintained | 3 | 4 | 12 | HIGH | All directors to complete AICD Company Directors Course or equivalent; annual governance review; legal briefing from Minter Ellison for new directors; Directors' & Officers' insurance |  |  | LOW | ACTIVE | 11764771273
Register 5: Compliance & Legal Risks |  |  | 11730774170
Subitems | Name | Category | Risk Description | Existing Controls | Likelihood | Consequence | Inherent Risk | Status | Treatment/Action | People | Residual Rating | Residual Risk | Status | Item ID (auto generated)
| C1 | Compliance | ACNC non-compliance — failure to meet reporting obligations, maintain charitable purpose, or comply with ACNC governance standards risks deregistration and loss of DGR status | Annual financial statements prepared by CFO w Pitcher Partners; governance policies being developed; Board oversight | 2 | 5 | 10 | MEDIUM | Implement ACNC compliance calendar; assign compliance responsibility to CEO; Board to review ACNC governance standards annually; legal advice from Minter Ellison |  | 5 | LOW | PLANNED | 11764796938
| C2 | Compliance | Food safety regulatory breach — failure to comply with Food Act 1984 (Vic) and Food Standards Australia New Zealand requirements in kitchen and café operations Fair Work Act obligations — payroll errors, non-payment of entitlements, or incorrect award classifications expose MWI to Fair Work claims and reputational damage | Head Chef with professional food safety accreditation; kitchen approved by local council; food safety practices in place | 2 | 5 | 10 | MEDIUM | Obtain Food Safety Supervisor certification for key staff; annual food safety audit; clear allergen management procedures; maintain council registration |  | 4 | LOW | ACTIVE | 11764818461
| C3 | Compliance | Fair Work Act obligations — payroll errors, non-payment of entitlements, or incorrect award classifications expose MWI to Fair Work claims and reputational damage | Pitcher Partners payroll oversight; superannuation provisions maintained; annual leave provisions recorded | 2 | 4 | 8 | MEDIUM | Annual payroll audit by Pitcher Partners; review award classifications for all roles; ensure employment contracts are current and compliant |  | 3 | LOW | ACTIVE | 11764821416
| C4 | Compliance | Privacy Act obligations — collection and storage of participant personal, health, and cultural information must comply with the Australian Privacy Act 1988 | Limited digital data storage; informal data handling practices currently in use | 3 | 3 | 9 | MEDIUM | Develop Privacy Policy; train staff on data handling; implement secure storage for participant records; conduct privacy impact assessment on new digital systems |  | 4 | LOW | PLANNED | 11764818568
| C5 | Compliance | Director conflict of interest — related party transactions (loans from Harris Ryan, Nikki Blanch) and founder involvement in operational decisions creates governance risk | Conflict of Interest Register maintained; policies being developed; Pitcher Partners financial oversight | 3 | 4 | 12 | HIGH | Formalise conflict of interest policy; require all directors to declare interests at each meeting; non-conflicted directors to approve related party transactions; legal review by Minter Ellison |  | 6 | MEDIUM | ACTIVE | 11764818881
Register 6: Reputational Risks |  |  | 11730783783
Subitems | Name | Category | Risk Description | Existing Controls | Likelihood | Consequence | Inherent Risk | Status | Treatment/Action | People | Residual Rating | Residual Risk | Status | Item ID (auto generated)
| R1 | Reputational | Negative media coverage — a food safety incident, governance failure, or programme harm event generates negative media attention damaging MWI's brand, funder relationships, and recruitment | Strong community reputation; Lendlease and QBE relationships positive; media exposure currently limited | 2 | 4 | 8 | MEDIUM | Develop crisis communications protocol; identify designated media spokesperson; Board Chair and CEO to be jointly briefed on any reputational incident; social media policy |  | 4 | LOW | PLANNED | 11764893975
| R2 | Reputational | Social media incident — negative social media post about MWI, its food, or its programme by a disgruntled participant, customer, or volunteer goes viral | Active positive social media presence; community goodwill high; corporate volunteers typically supportive | 2 | 4 | 8 | MEDIUM | Develop social media response policy; monitor brand mentions; designate social media manager with response authority; escalate any material issue to CEO within 2 hours |  | 3 | LOW | PLANNED | 11764835884
| R3 | Reputational | Safeguarding breach — a participant or staff member raises a concern about inappropriate conduct within the programme that, if mishandled, damages trust and reputation | Cultural safety embedded; diverse team; referral pathways in place | 2 | 5 | 10 | MEDIUM | Implement formal safeguarding and complaints handling policy; train all staff; establish confidential reporting channel; all complaints to be reported to Board |  | 4 | LOW | PLANNED | 11764857356
| R4 | Reputational | Funder relationship damage — failure to acquit a grant or meet reporting obligations causes a major funder (QBE, Stronger Enterprises) to withdraw or not renew | Pitcher Partners financial support; management team tracks deliverables; QBE relationship actively managed | 2 | 4 | 8 | MEDIUM | Implement grants management calendar; assign acquittal responsibility; CEO to proactively communicate with all major funders quarterly |  | 3 | LOW | ACTIVE | 11764813085
Register 7: Technology & Digital Risks |  |  | 11730790619
Subitems | Name | Category | Risk Description | Existing Controls | Likelihood | Consequence | Inherent Risk | Status | Treatment/Action | People | Residual Rating | Residual Risk | Status | Item ID (auto generated)
| T1 | Technology | SIK digital platform failure — remote management system for Social Impact Kiosk at Victoria Harbour fails, causing extended downtime and revenue loss | Machine supplier support line; Lendlease site access; Harris to research alternatives via Fellowship | 4 | 3 | 12 | HIGH | Negotiate minimum SLA with Spanish supplier; develop manual override protocol; evaluate local machine alternative (Harris Fellowship research) |  | 4 | LOW | ACTIVE | 11764819521
| T2 | Technology | Website and e-commerce failure — B2C/B2B ready-made meals website under development by Rachael Hua (1 day/week) is delayed, reducing commercial revenue pipeline | Rachael Hua engaged; development underway; minimal commercial loss until site is live | 3 | 3 | 9 | MEDIUM | Establish website launch milestone with Board; ensure backup technical support identified; test site thoroughly before go-live; data privacy review of e-commerce functionality |  | 4 | LOW | ACTIVE | 11764818877
| T3 | Technology | Data breach — participant or financial data accessed, lost, or stolen through cyber attack, physical theft, or accidental disclosure | Limited digital footprint; no major digital platform currently; Pitcher Partners financial system | 2 | 4 | 8 | MEDIUM | Implement cybersecurity basics (strong passwords, MFA, encrypted storage); develop data breach response plan; annual cybersecurity review; staff training |  | 3 | LOW | PLANNED | 11764894310